## Gantt Chart
CS350 Gantt Chart
Key Risks Outlined in Red
WBS NUMBER | PLAN (A = Target MVP, A+ = Extra, B = Backup) | TASK TITLE | START DATE | DUE DATE | ASSIGNED TO | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  | BREAK |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | SPRING BREAK |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
 | time axis 2026-02-09 to 2026-05-05
 | time axis 2026-02-09 to 2026-05-05
1 |  | Project Conception
1.1 | B | Setup backend libraries | 2/10 | 2/17 | All | 100% | bar: 2026-02-10 to 2026-02-16; 2026-03-30 to 2026-04-03; 2026-04-20 to 2026-04-21
1.1.1 | B | Setup frontend libraries | 2/10 | 2/17 | All | 100% | bar: 2026-02-10 to 2026-02-16; 2026-03-30 to 2026-04-03; 2026-04-20 to 2026-04-21
1.2 | B | Setup database software | 2/10 | 2/17 | All | 100% | bar: 2026-02-10 to 2026-02-16; 2026-03-30 to 2026-04-03; 2026-04-20 to 2026-04-21
1.3 | B | Connect with user / get live demo | 2/10 | 2/13 | All | 100% | bar: 2026-02-10 to 2026-02-24; 2026-03-30 to 2026-04-03; 2026-04-20 to 2026-04-21
2 |  | Backend Development
2.1 | A | Set up server | 2/24 | 4/13 | Gavin/JasonFred | 100% | bar: 2026-02-16; 2026-02-24 to 2026-04-13; 2026-04-20 to 2026-04-21
2.2 | A | Hosting | 3/11 | 5/5 | Jason | 100% | bar: 2026-02-16; 2026-02-24 to 2026-05-05
2.3 | B | Login/authentication system | 2/24 | 4/13 | Gavin, JasonFred | 100% | bar: 2026-02-16; 2026-02-24 to 2026-04-13; 2026-04-20 to 2026-04-21
3.1.1 | B | Admin Page | 4/2 | 4/13 | JasonFred | 100% | bar: 2026-02-16; 2026-03-30 to 2026-04-13; 2026-04-20 to 2026-04-21
2.4 | B | Patient case list & management | 3/14 | 3/27 | Gavin, JasonFred | 100% | bar: 2026-02-16; 2026-03-09 to 2026-04-03; 2026-04-20 to 2026-04-21
2.5 | B | Connect to front end | 3/23 | 3/ | All | 100% | bar: 2026-02-16; 2026-03-23 to 2026-04-03; 2026-04-20 to 2026-04-21
2.6 | B | Connect to database | 3/23 | 3/31 | Laney, Gavin, JasonFred | 100% | bar: 2026-02-16; 2026-03-23 to 2026-04-03; 2026-04-20 to 2026-04-21
2.7 | B | Testing/debugging/odds&ends | 4/1 | 5/5 | All | 0% | bar: 2026-02-16; 2026-03-30 to 2026-05-05
2.8 | A+ | File upload handling? | 4/1 | 4/21 | - | 60% | bar: 2026-02-16; 2026-03-30 to 2026-04-21
3 |  | Frontend Development
3.1 | B | Login page | 2/20 | 3/5 | Aniekan, Natalie, JasonFred | 100% | bar: 2026-02-16; 2026-02-20 to 2026-03-05; 2026-03-30 to 2026-04-03; 2026-04-20 to 2026-04-21
3.1.1 | B | Admin Page | 4/2 | 4/13 | JasonFred | 100% | bar: 2026-02-16; 2026-03-30 to 2026-04-13; 2026-04-20 to 2026-04-21
3.1.2 | B | Faculty dashboard | 3/27 | 4/13 | Natalie | 100% | bar: 2026-02-16; 2026-03-27 to 2026-04-13; 2026-04-20 to 2026-04-21
3.1.3.1 | B | Faculty view of student cases | 4/1 | 4/21 | Natalie | 100% | bar: 2026-02-16; 2026-03-30 to 2026-04-21
3.1.3.2 | B | Case template/editing | 4/1 | 4/21 | Natalie | 90% | bar: 2026-02-16; 2026-03-30 to 2026-04-21
3.1.2 | B | Student page | 3/23 | 3/30 | Aniekan, Laney | 100% | bar: 2026-02-16; 2026-03-27 to 2026-04-13; 2026-04-20 to 2026-04-21
3.2 | B | Testing/debugging/odds&ends | 4/1 | 5/5 | All | 50% | bar: 2026-02-16; 2026-03-30 to 2026-05-05
3.3 | B | Notetaking | 3/23 | 4/1 | Aniekan | 100% | bar: 2026-02-16; 2026-03-23 to 2026-04-21
3.3.1 | A+ | Grades & Feedback | 4/6 | 4/13 | Aniekan | 100% | bar: 2026-02-16; 2026-03-30 to 2026-04-13; 2026-04-20 to 2026-04-21
3.4 | A+ | PBL/SIM Case | 4/6 | 4/13 | Aniekan | 100% | bar: 2026-02-16; 2026-03-30 to 2026-04-13; 2026-04-20 to 2026-04-21
3.4.1 | A+ | Drop Down | 4/6 | 4/13 | Laney, Aniekan | 100% | bar: 2026-02-16; 2026-03-30 to 2026-04-13; 2026-04-20 to 2026-04-21
4 |  | Database Devlopment
4.1 | B | Set up postgre sql | 2/10 | 2/17 | Laney | 100% | bar: 2026-02-10 to 2026-02-16; 2026-03-30 to 2026-04-03; 2026-04-20 to 2026-04-21
4.2 | A | Get test data | 2/10 | 2/25 | All | 100% | bar: 2026-02-10 to 2026-02-25; 2026-03-30 to 2026-04-03; 2026-04-20 to 2026-04-21
4.3 | B | Setup table organization | 3/3 | 3/15 | Laney | 100% | bar: 2026-02-16; 2026-03-03 to 2026-03-13; 2026-03-30 to 2026-04-03; 2026-04-20 to 2026-04-21
4.4 | B | Connect to the back and front end | 3/18 | 3/27 | Jason | 100% | bar: 2026-02-16; 2026-03-18 to 2026-04-03; 2026-04-20 to 2026-04-21